## TPL Comments
Sr No. | Submittal | Document | Customer Comments | Xylem Remarks
1 | SUB1445 | TPL-D02-253-XYLM-WTP-003_Pump Technical Data sheet for CWTP |  | Comment not Received
2 | SUB1446 | TPL-D02-253-XYLM-WTP-004_Motor Data sheet for CWTP | Option Variant Codes / Definition
3 | SUB1448 | TPL-D02-253-XYLM-WTP-006_VFD Technical Data sheet & General Arrangement Drawing for CWTP |  | Comment not Received
4 | SUB1449 | TPL-D02-253-XYLM-WTP-007_Skid General Arrangement Drawing for CWTP |  | Comment not Received
5 | SUB1502 | TPL-D02-253-XYLM-WTP-009_Bellow Technical Data sheet & General Arrangement Drawing for CWTP |  | Comment not Received
6 | SUB1529 | TPL-D02-253-XYLM-WTP-015_Motor Data sheet for IWFP | Option Variant Codes / Definition
7 | SUB1530 | TPL-D02-253-XYLM-WTP-016_Motor General Arrangement Drawing for IWFP |  | Comment not Received
8 | SUB1531 | TPL-D02-253-XYLM-WTP-017_VFD Technical Data sheet & General Arrangement Drawing for IWFP |  | Comment not Received
9 | SUB1576 | TPL-D02-253-XYLM-WTP-014_Pump Technical Data sheet for IWFP | 10. Pumps selection: 15% capacity increase shall be by changing impeller only with the same
motor frame. Pumps
should have spare capacity at least of 15%
Insert text here
9. Pumps must meet minimum 80% efficiency.
10 | SUB1577 | TPL-D02-253-XYLM-WTP-018_Skid General Arrangement Drawing for IWFP | Compare with P&ID , The instrument instalation point, sampling valve point missing in the drawing.
11 | SUB1578 | TPL-D02-253-XYLM-WTP-023_Valve Data sheet General Arrangement Drawing for IWFP | Complete details are not available, including the tag number and valve location on the skid. Only the check valve datasheet is available, and other valve details are missing. Please also confirm whether this valve was procured from an approved vendor.
12 | SUB1579 | TPL-D02-253-XYLM-WTP-025_Pump Technical Data sheet for UPWFP | Pump Efficiency min 80% Pumps selection: 15% capacity increase shall be by changing impeller only with the same motor frame. Pumps should have spare capacity at least of 15%
13 | SUB1580 | TPL-D02-253-XYLM-WTP-036_Pump Technical Data sheet for DWTP | Pumps selection: 15% capacity increase shall be by changing impeller only with the same motor frame. Pumps should have spare capacity at least of 15%. Pumps must meet minimum 80% efficiency.
14 | SUB1614 | TPL-D02-253-XYLM-WTP-024_Pumps General Arrangement Drawing for UPWFP | Pump data sheet mention EN standard, But here show IS class, have confusion?
15 | SUB1615 | TPL-D02-253-XYLM-WTP-026_Motor Data sheet for UPWFP | Option Variant Codes / Definition
16 | SUB1616 | TPL-D02-253-XYLM-WTP-027_Motor General Arrangement Drawing for UPWFP | Please incorporate following detail , 1. Vibration Isolator 2. Motor name plate information 3. Accelerometer for Vibration analysis & control
17 | SUB1617 | TPL-D02-253-XYLM-WTP-028_VFD Technical Data sheet & General Arrangement Drawing for UPWFP | Confirm the compliance to project specification Variable Frequency Motor Controllers ( 26 29 23 ) clause 2.4 / A , i.e. Full digital control of frequency and voltage with seven-segment HMI installed on VFD enclosure providing programming, monitoring, alarms, adjustment, and control features including: 1. Manual/Off/Auto selector with bump less transfer. 2. Local manual speed, start, stop, reset controls. 3. Local or remote speed reference selector for bump less transfer via programmable acceleration/deceleration rates. 4. Adjustment of speed, rate of change, dc boost, current limit, frequency skip. 5. Run, Fault Indication Lamps. 6. Local Start/Stop Push Button, one Emergency (stay put lockable type) Push Button. 7. Remote start-stop control capability via contact. 8. Monitoring of current, frequency, voltage, and speed. 9. Drive diagnostics. 10. Option for remote mounting of keypad.
Wiring for motor thermistor
Confirm communication port type for Modbus RTU (RS485) ie. RJ45 or 9-pin (SUB-D)
Please note that the LT voltage level is 433V (±5%); the vendor needs to verify all components accordingly.
Confirm the compliance to project specification and IO LIST for Interfaces between VFD and RIO PANEL via hardwire: DO Start Command from PLC -1 EM / Stop Command from PLC -1 DI LCP / Remote Status Indication to PLC 2 Running Status Indication to PLC - 1 EM / TRIP / Fault Indication to PLC - 1 AI Analog Speed setpoint from PLC AO Analog Speed feedback to PLC RS485 interface at single point to all VFD
18 | SUB1618 | TPL-D02-253-XYLM-WTP-029_Skid General Arrangement Drawing for UPWFP | Same comment from previous submital, Instrument fitting and sampling line missing
19 | SUB1619 | TPL-D02-253-XYLM-WTP-030_Vibration isolator Data sheet for UPWFP | Our area falls under Seismic Zone 4. If the vendor proposes a single spring support, will it be sufficient to arrest vibration? We require supporting calculations to justify the use of a single spring.
20 | SUB1620 | TPL-D02-253-XYLM-WTP-031_Bellow Technical Data sheet & General Arrangement Drawing for UPWFP | Attached general data sheet, Do not index to show, what they are going to use in our DF1 project, no clear information.
21 | SUB1622 | TPL-D02-253-XYLM-WTP-034_Valve Data sheet General Arrangement Drawing for UPWFP | 1.Only have check valve drawing, other valves in the skid missing,
2. Location of the using the valve and Tag number missing in the list
22 | SUB1712 | TPL-D02-253-XYLM-WTP-035_Pumps General Arrangement Drawing for DWTP | Please submit a proper and complete GA (General Arrangement) drawing. Currently, only numerical values are visible, and the descriptions/labels are missing. Not accetable
23 | SUB1713 | TPL-D02-253-XYLM-WTP-037_Motor Data sheet for DWTP | Option Variant Codes / Definition
24 | SUB1714 | TPL-D02-253-XYLM-WTP-038_Motor General Arrangement Drawing for DWTP |  | Comment not Received
25 | SUB1715 | TPL-D02-253-XYLM-WTP-039_VFD Technical Data sheet & General Arrangement Drawing for DWTP |  | Comment not Received
26 | SUB1716 | TPL-D02-253-XYLM-WTP-040_Skid General Arrangement Drawing for DWTP | Based on P&ID missing item in the skid drawing — 1.DPT connection point & Valve,
2.Pump inlet and outlet sampling point
3. PG connection point
The reference drawing should not be submitted for approval. Only the confirmation drawing is to be submitted for approval.
27 | SUB1718 | TPL-D02-253-XYLM-WTP-042_Bellow Technical Data sheet & General Arrangement Drawing for DWTP | Not clear in the document, — 1. the bellow type,
2. Model
3.Sezing
4.Matterial
5. Any coating or lining
All above details not clear in the docuemnt
28 | SUB1720 | TPL-D02-253-XYLM-WTP-045_Valve Data sheet General Arrangement Drawing for DWTP | The cover datasheet missing in the document — 1. Valve tag number
2.Valve location of the skid
3. Size of the valve using DF1 2.0 project
4, Valve Type
5.How many quantity
6.Etc

## Debug - All Annotations
Submittal | File | Page | Annotation Type | Author | Content (raw) | Classified As
SUB1445 | 001_Pump Technical Data sheet for CWTP (WTP2-VFD-101 A-B-C-D).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1445 | 001_Pump Technical Data sheet for CWTP (WTP2-VFD-101 A-B-C-D).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1446 | 001_Motor Data sheet for CWTP (WTP2-VFD-101 A-B-C-D).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1446 | 001_Motor Data sheet for CWTP (WTP2-VFD-101 A-B-C-D).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1446 | 001_Motor Data sheet for CWTP (WTP2-VFD-101 A-B-C-D).pdf | 3 | RedText (embedded) | Reviewer (red ink) | Option Variant Codes / Definition | ✅ COMMENT
SUB1448 | 001_VFD Technical Data sheet & General Arrangement Drawing for CWTP (WTP2-VFD-101 A-B-C-D).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1448 | 001_VFD Technical Data sheet & General Arrangement Drawing for CWTP (WTP2-VFD-101 A-B-C-D).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1449 | 001_Skid General Arrangement Drawing for CWTP (WTP2-VFD-101 A-B-C-D).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1449 | 001_Skid General Arrangement Drawing for CWTP (WTP2-VFD-101 A-B-C-D).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1449 | 001_Skid General Arrangement Drawing for CWTP (WTP2-VFD-101 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | 2"FOR PULMBING PIPE SUCTION | ⛔ Not a comment
SUB1449 | 001_Skid General Arrangement Drawing for CWTP (WTP2-VFD-101 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | 8 | ⛔ Not a comment
SUB1449 | 001_Skid General Arrangement Drawing for CWTP (WTP2-VFD-101 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | 1 | ⛔ Not a comment
SUB1449 | 001_Skid General Arrangement Drawing for CWTP (WTP2-VFD-101 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | 2 | ⛔ Not a comment
SUB1449 | 001_Skid General Arrangement Drawing for CWTP (WTP2-VFD-101 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | 3 | ⛔ Not a comment
SUB1449 | 001_Skid General Arrangement Drawing for CWTP (WTP2-VFD-101 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | 4 | ⛔ Not a comment
SUB1449 | 001_Skid General Arrangement Drawing for CWTP (WTP2-VFD-101 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | 5 | ⛔ Not a comment
SUB1449 | 001_Skid General Arrangement Drawing for CWTP (WTP2-VFD-101 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | 6 | ⛔ Not a comment
SUB1449 | 001_Skid General Arrangement Drawing for CWTP (WTP2-VFD-101 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | 7 | ⛔ Not a comment
SUB1449 | 001_Skid General Arrangement Drawing for CWTP (WTP2-VFD-101 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | 9 | ⛔ Not a comment
SUB1449 | 001_Skid General Arrangement Drawing for CWTP (WTP2-VFD-101 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | 10 | ⛔ Not a comment
SUB1449 | 001_Skid General Arrangement Drawing for CWTP (WTP2-VFD-101 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | 11 | ⛔ Not a comment
SUB1449 | 001_Skid General Arrangement Drawing for CWTP (WTP2-VFD-101 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | 12 | ⛔ Not a comment
SUB1449 | 001_Skid General Arrangement Drawing for CWTP (WTP2-VFD-101 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | 13 | ⛔ Not a comment
SUB1449 | 001_Skid General Arrangement Drawing for CWTP (WTP2-VFD-101 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | 14 | ⛔ Not a comment
SUB1449 | 001_Skid General Arrangement Drawing for CWTP (WTP2-VFD-101 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | 15 | ⛔ Not a comment
SUB1449 | 001_Skid General Arrangement Drawing for CWTP (WTP2-VFD-101 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | 16 | ⛔ Not a comment
SUB1449 | 001_Skid General Arrangement Drawing for CWTP (WTP2-VFD-101 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | 18 | ⛔ Not a comment
SUB1449 | 001_Skid General Arrangement Drawing for CWTP (WTP2-VFD-101 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | 17 | ⛔ Not a comment
SUB1449 | 001_Skid General Arrangement Drawing for CWTP (WTP2-VFD-101 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | 19 | ⛔ Not a comment
SUB1502 | 001_Bellow Technical Data sheet & General Arrangement Drawing for CWTP (WTP2-VFD-101 A-B-C-D).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1502 | 001_Bellow Technical Data sheet & General Arrangement Drawing for CWTP (WTP2-VFD-101 A-B-C-D).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1502 | 001_Bellow Technical Data sheet & General Arrangement Drawing for CWTP (WTP2-VFD-101 A-B-C-D).pdf | 6 | Highlight |  |  | ⛔ Not a comment
SUB1529 | 001_Motor Data sheet for IWFP(WTP1-VFD-601 A-B-C-D)_annotated.pdf | 3 | RedText (embedded) | Reviewer (red ink) | Option Variant Codes / Definition | ✅ COMMENT
SUB1529 | 001_Motor Data sheet for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1529 | 001_Motor Data sheet for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1529 | 001_Motor Data sheet for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 3 | RedText (embedded) | Reviewer (red ink) | Option Variant Codes / Definition | ✅ COMMENT
SUB1530 | 001_Motor General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1530 | 001_Motor General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1531 | 001_VFD Technical Data sheet & General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1531 | 001_VFD Technical Data sheet & General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1576 | 001_Pump Technical Data sheet for IWFP(WTP1-VFD-601 A-B-C-D)_annotated.pdf | 5 | RedText (embedded) | Reviewer (red ink) | 10. Pumps selection: 15% capacity increase shall be by changing impeller only with the same ¦ motor frame. Pumps ¦ should have spare capacity at least of 15% | ✅ COMMENT
SUB1576 | 001_Pump Technical Data sheet for IWFP(WTP1-VFD-601 A-B-C-D)_annotated.pdf | 6 | RedText (embedded) | Reviewer (red ink) | Insert text here | ✅ COMMENT
SUB1576 | 001_Pump Technical Data sheet for IWFP(WTP1-VFD-601 A-B-C-D)_annotated.pdf | 7 | RedText (embedded) | Reviewer (red ink) | 9. Pumps must meet minimum 80% efficiency. | ✅ COMMENT
SUB1576 | 001_Pump Technical Data sheet for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1576 | 001_Pump Technical Data sheet for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 8 | Line |  |  | ⛔ Not a comment
SUB1576 | 001_Pump Technical Data sheet for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 8 | Line |  |  | ⛔ Not a comment
SUB1576 | 001_Pump Technical Data sheet for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 8 | Line |  |  | ⛔ Not a comment
SUB1576 | 001_Pump Technical Data sheet for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 8 | Line |  |  | ⛔ Not a comment
SUB1576 | 001_Pump Technical Data sheet for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 8 | Line |  |  | ⛔ Not a comment
SUB1576 | 001_Pump Technical Data sheet for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 8 | Line |  |  | ⛔ Not a comment
SUB1577 | 001_Skid General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D)_annotated.pdf | 2 | RedText (embedded) | Reviewer (red ink) | Compare with P&ID , The instrument instalation point, sampling valve point missing in the drawing. | ✅ COMMENT
SUB1577 | 001_Skid General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1577 | 001_Skid General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1578 | 001_Valve Data sheet General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D)_annotated.pdf | 3 | RedText (embedded) | Reviewer (red ink) | Complete details are not available, including the tag number and valve location on the skid. Only the check valve datasheet ¦ is available, and other valve details are missing. Please also confirm whe | ✅ COMMENT
SUB1578 | 001_Valve Data sheet General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1578 | 001_Valve Data sheet General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | ALL DIMENSION ARE IN MM | ⛔ Not a comment
SUB1578 | 001_Valve Data sheet General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | 01 | ⛔ Not a comment
SUB1578 | 001_Valve Data sheet General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | BODY | ⛔ Not a comment
SUB1578 | 001_Valve Data sheet General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | WCB | ⛔ Not a comment
SUB1578 | 001_Valve Data sheet General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | 02 | ⛔ Not a comment
SUB1578 | 001_Valve Data sheet General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | DISC | ⛔ Not a comment
SUB1578 | 001_Valve Data sheet General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | CF8 | ⛔ Not a comment
SUB1578 | 001_Valve Data sheet General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | 03 | ⛔ Not a comment
SUB1578 | 001_Valve Data sheet General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | SEAT RING | ⛔ Not a comment
SUB1578 | 001_Valve Data sheet General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | VITON | ⛔ Not a comment
SUB1578 | 001_Valve Data sheet General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | 04 | ⛔ Not a comment
SUB1578 | 001_Valve Data sheet General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | SS304 | ⛔ Not a comment
SUB1578 | 001_Valve Data sheet General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | 05 | ⛔ Not a comment
SUB1578 | 001_Valve Data sheet General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | STOP PIN & HINGE PIN | ⛔ Not a comment
SUB1578 | 001_Valve Data sheet General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | SS304 | ⛔ Not a comment
SUB1578 | 001_Valve Data sheet General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | 06 | ⛔ Not a comment
SUB1578 | 001_Valve Data sheet General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | PIN LOCK NUT | ⛔ Not a comment
SUB1578 | 001_Valve Data sheet General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | S.S | ⛔ Not a comment
SUB1578 | 001_Valve Data sheet General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | 07 | ⛔ Not a comment
SUB1578 | 001_Valve Data sheet General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | SPACER WASHER | ⛔ Not a comment
SUB1578 | 001_Valve Data sheet General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | SS 304 | ⛔ Not a comment
SUB1578 | 001_Valve Data sheet General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | 08 | ⛔ Not a comment
SUB1578 | 001_Valve Data sheet General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | SPACE BUSH | ⛔ Not a comment
SUB1578 | 001_Valve Data sheet General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | S.S 304 & PTFE | ⛔ Not a comment
SUB1578 | 001_Valve Data sheet General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | 09 | ⛔ Not a comment
SUB1578 | 001_Valve Data sheet General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | PACKING WASHER | ⛔ Not a comment
SUB1578 | 001_Valve Data sheet General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 3 | Square | AutoCAD SHX Text | NBR | ⛔ Not a comment
SUB1578 | 001_Valve Data sheet General Arrangement Drawing for IWFP(WTP1-VFD-601 A-B-C-D).pdf | 3 | Highlight |  |  | ⛔ Not a comment
SUB1579 | 001_Pump Technical Data sheet for UPWFP (WTP1-VFD-701 A-B-C-D-E)_annotated.pdf | 5 | RedText (embedded) | Reviewer (red ink) | Pump Efficiency min 80% ¦ Pumps selection: 15% capacity increase shall be by changing impeller only with the same motor ¦ frame. Pumps ¦ should have spare capacity at least of 15% | ✅ COMMENT
SUB1579 | 001_Pump Technical Data sheet for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1579 | 001_Pump Technical Data sheet for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 8 | Line |  |  | ⛔ Not a comment
SUB1579 | 001_Pump Technical Data sheet for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 8 | Line |  |  | ⛔ Not a comment
SUB1579 | 001_Pump Technical Data sheet for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 8 | Line |  |  | ⛔ Not a comment
SUB1579 | 001_Pump Technical Data sheet for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 8 | Line |  |  | ⛔ Not a comment
SUB1579 | 001_Pump Technical Data sheet for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 8 | Line |  |  | ⛔ Not a comment
SUB1579 | 001_Pump Technical Data sheet for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 8 | Line |  |  | ⛔ Not a comment
SUB1580 | 001_Pump Technical Data sheet for DWTP(WTP1-VFD-901 A-B-C)_annotated.pdf | 4 | RedText (embedded) | Reviewer (red ink) | Pumps selection: 15% capacity increase shall be by changing impeller only with the same motor ¦ frame. Pumps ¦ should have spare capacity at least of 15%. ¦ Pumps must meet minimum 80% efficiency. | ✅ COMMENT
SUB1580 | 001_Pump Technical Data sheet for DWTP(WTP1-VFD-901 A-B-C).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1614 | 001_Pumps General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E)_annotated.pdf | 3 | RedText (embedded) | Reviewer (red ink) | Pump data sheet mention EN standard, But here show IS class, have confusion? | ✅ COMMENT
SUB1614 | 001_Pumps General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1615 | 001_Motor Data sheet for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1615 | 001_Motor Data sheet for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 3 | RedText (embedded) | Reviewer (red ink) | Option Variant Codes / Definition | ✅ COMMENT
SUB1616 | SUB1616_Response 1.pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1616 | SUB1616_Response 1.pdf | 4 | FreeText | TPL20390 | Please incorporate following detail , 1. Vibration Isolator 2. Motor name plate information 3. Accelerometer for Vibration analysis & control | ✅ COMMENT
SUB1616 | 001_Motor General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1617 | SUB1617_Response 1.pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1617 | SUB1617_Response 1.pdf | 2 | FreeText | TPL19168 | Confirm the compliance to project specification Variable Frequency Motor Controllers ( 26 29 23 ) clause 2.4 / A , i.e. Full digital control of frequency and voltage with seven-segment HMI installed o | ✅ COMMENT
SUB1617 | SUB1617_Response 1.pdf | 4 | FreeText | TPL19168 | Wiring for motor thermistor | ✅ COMMENT
SUB1617 | SUB1617_Response 1.pdf | 4 | FreeText | TPL19168 | Confirm communication port type for Modbus RTU (RS485) ie. RJ45 or 9-pin (SUB-D) | ✅ COMMENT
SUB1617 | SUB1617_Response 1.pdf | 5 | FreeText | TPL19168 | Confirm the compliance to project specification Variable Frequency Motor Controllers ( 26 29 23 ) clause 2.4 / B , i.e Interfaces provisions 1. Modbus RTU (RS485) communication port for VFD paramete | ✅ COMMENT
SUB1617 | SUB1617_Response 1.pdf | 18 | FreeText | TPL20390 | Please note that the LT voltage level is 433V (±5%); the vendor needs to verify all components accordingly. | ✅ COMMENT
SUB1617 | SUB1617_Response 1.pdf | 22 | Square | TPL20390 |  | ⛔ Not a comment
SUB1617 | SUB1617_Response 1.pdf | 36 | FreeText | TPL19168 | Confirm the compliance to project specification Variable Frequency Motor Controllers ( 26 29 23 ) clause 2.4 / B , i.e C. Interfaces between VFD and optional Local Control Box (for VFDs installed in r | ✅ COMMENT
SUB1617 | SUB1617_Response 1.pdf | 37 | Square | TPL20390 |  | ⛔ Not a comment
SUB1617 | SUB1617_Response 1.pdf | 37 | Square | TPL20390 |  | ⛔ Not a comment
SUB1617 | SUB1617_Response 1.pdf | 38 | FreeText | TPL19168 | Confirm the compliance to project specification and IO LIST for Interfaces between VFD and RIO PANEL via hardwire: DO Start Command from PLC -1 EM / Stop Command from PLC -1 DI LCP / Remote Status | ✅ COMMENT
SUB1617 | 001_VFD Technical Data sheet & General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1618 | 001_Skid General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E)_annotated.pdf | 3 | RedText (embedded) | Reviewer (red ink) | Same comment from previous submital, Instrument fitting and sampling line missing | ✅ COMMENT
SUB1618 | 001_Skid General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1619 | 001_Vibration isolator Data sheet for UPWFP (WTP1-VFD-701 A-B-C-D-E)_annotated.pdf | 2 | RedText (embedded) | Reviewer (red ink) | Our area falls under Seismic Zone 4. If the vendor proposes a single spring support, will it be ¦ sufficient to arrest vibration? We require supporting calculations to justify the use of a single ¦ sp | ✅ COMMENT
SUB1619 | 001_Vibration isolator Data sheet for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1619 | 001_Vibration isolator Data sheet for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 4 | Highlight |  |  | ⛔ Not a comment
SUB1620 | 001_Bellow Technical Data sheet & General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-_annotated.pdf | 2 | RedText (embedded) | Reviewer (red ink) | Attached general data sheet, ¦ Do not index to show, what they are going to use in our DF1 project, no clear information. | ✅ COMMENT
SUB1620 | 001_Bellow Technical Data sheet & General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-.pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1620 | 001_Bellow Technical Data sheet & General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-.pdf | 6 | Highlight |  |  | ⛔ Not a comment
SUB1622 | 001_Valve Data sheet General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E)_annotated.pdf | 3 | RedText (embedded) | Reviewer (red ink) | 1.Only have check valve drawing, other valves in the skid missing, ¦ 2. Location of the using the valve and Tag number missing in the list | ✅ COMMENT
SUB1622 | 001_Valve Data sheet General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1622 | 001_Valve Data sheet General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 3 | Square | AutoCAD SHX Text | ALL DIMENSION ARE IN MM | ⛔ Not a comment
SUB1622 | 001_Valve Data sheet General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 3 | Square | AutoCAD SHX Text | 01 | ⛔ Not a comment
SUB1622 | 001_Valve Data sheet General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 3 | Square | AutoCAD SHX Text | BODY | ⛔ Not a comment
SUB1622 | 001_Valve Data sheet General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 3 | Square | AutoCAD SHX Text | WCB | ⛔ Not a comment
SUB1622 | 001_Valve Data sheet General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 3 | Square | AutoCAD SHX Text | 02 | ⛔ Not a comment
SUB1622 | 001_Valve Data sheet General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 3 | Square | AutoCAD SHX Text | DISC | ⛔ Not a comment
SUB1622 | 001_Valve Data sheet General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 3 | Square | AutoCAD SHX Text | CF8 | ⛔ Not a comment
SUB1622 | 001_Valve Data sheet General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 3 | Square | AutoCAD SHX Text | 03 | ⛔ Not a comment
SUB1622 | 001_Valve Data sheet General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 3 | Square | AutoCAD SHX Text | SEAT RING | ⛔ Not a comment
SUB1622 | 001_Valve Data sheet General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 3 | Square | AutoCAD SHX Text | VITON | ⛔ Not a comment
SUB1622 | 001_Valve Data sheet General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 3 | Square | AutoCAD SHX Text | 04 | ⛔ Not a comment
SUB1622 | 001_Valve Data sheet General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 3 | Square | AutoCAD SHX Text | SS304 | ⛔ Not a comment
SUB1622 | 001_Valve Data sheet General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 3 | Square | AutoCAD SHX Text | 05 | ⛔ Not a comment
SUB1622 | 001_Valve Data sheet General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 3 | Square | AutoCAD SHX Text | STOP PIN & HINGE PIN | ⛔ Not a comment
SUB1622 | 001_Valve Data sheet General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 3 | Square | AutoCAD SHX Text | SS304 | ⛔ Not a comment
SUB1622 | 001_Valve Data sheet General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 3 | Square | AutoCAD SHX Text | 06 | ⛔ Not a comment
SUB1622 | 001_Valve Data sheet General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 3 | Square | AutoCAD SHX Text | PIN LOCK NUT | ⛔ Not a comment
SUB1622 | 001_Valve Data sheet General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 3 | Square | AutoCAD SHX Text | S.S | ⛔ Not a comment
SUB1622 | 001_Valve Data sheet General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 3 | Square | AutoCAD SHX Text | 07 | ⛔ Not a comment
SUB1622 | 001_Valve Data sheet General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 3 | Square | AutoCAD SHX Text | SPACER WASHER | ⛔ Not a comment
SUB1622 | 001_Valve Data sheet General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 3 | Square | AutoCAD SHX Text | SS 304 | ⛔ Not a comment
SUB1622 | 001_Valve Data sheet General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 3 | Square | AutoCAD SHX Text | 08 | ⛔ Not a comment
SUB1622 | 001_Valve Data sheet General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 3 | Square | AutoCAD SHX Text | SPACE BUSH | ⛔ Not a comment
SUB1622 | 001_Valve Data sheet General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 3 | Square | AutoCAD SHX Text | S.S 304 & PTFE | ⛔ Not a comment
SUB1622 | 001_Valve Data sheet General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 3 | Square | AutoCAD SHX Text | 09 | ⛔ Not a comment
SUB1622 | 001_Valve Data sheet General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 3 | Square | AutoCAD SHX Text | PACKING WASHER | ⛔ Not a comment
SUB1622 | 001_Valve Data sheet General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 3 | Square | AutoCAD SHX Text | NBR | ⛔ Not a comment
SUB1622 | 001_Valve Data sheet General Arrangement Drawing for UPWFP (WTP1-VFD-701 A-B-C-D-E).pdf | 3 | Highlight |  |  | ⛔ Not a comment
SUB1712 | 001_Pumps General Arrangement Drawing for DWTP(WTP1-VFD-901 A-B-C)_annotated.pdf | 3 | RedText (embedded) | Reviewer (red ink) | Please submit a proper and complete GA (General Arrangement) drawing. ¦ Currently, only numerical values are visible, and the descriptions/labels are missing. ¦ Not accetable | ✅ COMMENT
SUB1712 | 001_Pumps General Arrangement Drawing for DWTP(WTP1-VFD-901 A-B-C).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1713 | 001_Motor Data sheet for DWTP(WTP1-VFD-901 A-B-C)_annotated.pdf | 3 | RedText (embedded) | Reviewer (red ink) | Option Variant Codes / Definition | ✅ COMMENT
SUB1713 | 001_Motor Data sheet for DWTP(WTP1-VFD-901 A-B-C).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1713 | 001_Motor Data sheet for DWTP(WTP1-VFD-901 A-B-C).pdf | 3 | RedText (embedded) | Reviewer (red ink) | Option Variant Codes / Definition | ✅ COMMENT
SUB1714 | 001_Motor General Arrangement Drawing for DWTP(WTP1-VFD-901 A-B-C).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1715 | 001_VFD Technical Data sheet & General Arrangement Drawing for DWTP(WTP1-VFD-901 A-B-C).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1716 | 001_Skid General Arrangement Drawing for DWTP(WTP1-VFD-901 A-B-C)_annotated.pdf | 3 | RedText (embedded) | Reviewer (red ink) | Based on P&ID missing item in the skid drawing ¦ 1.DPT connection point & Valve, ¦ 2.Pump inlet and outlet sampling point ¦ 3. PG connection point ¦ The reference drawing should not be submitted for a | ✅ COMMENT
SUB1716 | 001_Skid General Arrangement Drawing for DWTP(WTP1-VFD-901 A-B-C).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1716 | 001_Skid General Arrangement Drawing for DWTP(WTP1-VFD-901 A-B-C).pdf | 3 | Square | AutoCAD SHX Text | 12 | ⛔ Not a comment
SUB1716 | 001_Skid General Arrangement Drawing for DWTP(WTP1-VFD-901 A-B-C).pdf | 3 | Square | AutoCAD SHX Text | 1 | ⛔ Not a comment
SUB1716 | 001_Skid General Arrangement Drawing for DWTP(WTP1-VFD-901 A-B-C).pdf | 3 | Square | AutoCAD SHX Text | 2 | ⛔ Not a comment
SUB1716 | 001_Skid General Arrangement Drawing for DWTP(WTP1-VFD-901 A-B-C).pdf | 3 | Square | AutoCAD SHX Text | 3 | ⛔ Not a comment
SUB1716 | 001_Skid General Arrangement Drawing for DWTP(WTP1-VFD-901 A-B-C).pdf | 3 | Square | AutoCAD SHX Text | 4 | ⛔ Not a comment
SUB1716 | 001_Skid General Arrangement Drawing for DWTP(WTP1-VFD-901 A-B-C).pdf | 3 | Square | AutoCAD SHX Text | 5 | ⛔ Not a comment
SUB1716 | 001_Skid General Arrangement Drawing for DWTP(WTP1-VFD-901 A-B-C).pdf | 3 | Square | AutoCAD SHX Text | 6 | ⛔ Not a comment
SUB1716 | 001_Skid General Arrangement Drawing for DWTP(WTP1-VFD-901 A-B-C).pdf | 3 | Square | AutoCAD SHX Text | 7 | ⛔ Not a comment
SUB1716 | 001_Skid General Arrangement Drawing for DWTP(WTP1-VFD-901 A-B-C).pdf | 3 | Square | AutoCAD SHX Text | 8 | ⛔ Not a comment
SUB1716 | 001_Skid General Arrangement Drawing for DWTP(WTP1-VFD-901 A-B-C).pdf | 3 | Square | AutoCAD SHX Text | 9 | ⛔ Not a comment
SUB1716 | 001_Skid General Arrangement Drawing for DWTP(WTP1-VFD-901 A-B-C).pdf | 3 | Square | AutoCAD SHX Text | 10 | ⛔ Not a comment
SUB1716 | 001_Skid General Arrangement Drawing for DWTP(WTP1-VFD-901 A-B-C).pdf | 3 | Square | AutoCAD SHX Text | 11 | ⛔ Not a comment
SUB1716 | 001_Skid General Arrangement Drawing for DWTP(WTP1-VFD-901 A-B-C).pdf | 3 | Square | AutoCAD SHX Text | 13 | ⛔ Not a comment
SUB1716 | 001_Skid General Arrangement Drawing for DWTP(WTP1-VFD-901 A-B-C).pdf | 3 | Square | AutoCAD SHX Text | 14 | ⛔ Not a comment
SUB1716 | 001_Skid General Arrangement Drawing for DWTP(WTP1-VFD-901 A-B-C).pdf | 3 | Square | AutoCAD SHX Text | 15 | ⛔ Not a comment
SUB1716 | 001_Skid General Arrangement Drawing for DWTP(WTP1-VFD-901 A-B-C).pdf | 3 | Square | AutoCAD SHX Text | 16 | ⛔ Not a comment
SUB1716 | 001_Skid General Arrangement Drawing for DWTP(WTP1-VFD-901 A-B-C).pdf | 3 | Square | AutoCAD SHX Text | 17 | ⛔ Not a comment
SUB1716 | 001_Skid General Arrangement Drawing for DWTP(WTP1-VFD-901 A-B-C).pdf | 3 | Square | AutoCAD SHX Text | 18 | ⛔ Not a comment
SUB1718 | 001_Bellow Technical Data sheet & General Arrangement Drawing for DWTP(WTP1-VFD-901 A-B-C)_annotated.pdf | 2 | RedText (embedded) | Reviewer (red ink) | Not clear in the document, ¦ 1. the bellow type, ¦ 2. Model ¦ 3.Sezing ¦ 4.Matterial ¦ 5. Any coating or lining ¦ All above details not clear in the docuemnt | ✅ COMMENT
SUB1718 | 001_Bellow Technical Data sheet & General Arrangement Drawing for DWTP(WTP1-VFD-901 A-B-C).pdf | 1 | Stamp | USER |  | ⛔ Not a comment
SUB1718 | 001_Bellow Technical Data sheet & General Arrangement Drawing for DWTP(WTP1-VFD-901 A-B-C).pdf | 6 | Highlight |  |  | ⛔ Not a comment
SUB1720 | 001_Valve Data sheet General Arrangement Drawing for DWTP(WTP1-VFD-901 A-B-C)_annotated.pdf | 2 | RedText (embedded) | Reviewer (red ink) | The cover datasheet missing in the document ¦ 1. Valve tag number ¦ 2.Valve location of the skid ¦ 3. Size of the valve using DF1 2.0 project ¦ 4, Valve Type ¦ 5.How many quantity ¦ 6.Etc | ✅ COMMENT
SUB1720 | 001_Valve Data sheet General Arrangement Drawing for DWTP(WTP1-VFD-901 A-B-C).pdf | 1 | Stamp | USER |  | ⛔ Not a comment